## Digitisation Cost Estimator
IMPACT Digitisation Cost Estimator
Version 3.06, January 2011
Provided by Gottingen State and University Library
1. DEFINE BASIC PARAMETERS
# of volumes | 3000
# of total pages to be imaged | 4500000
storage space per page incl. surrogates (Mb.) | 40
cost of storage per terabyte | 500
working days in a year for FTE | 220
working hours in a day for FTE | 8
QA overhead | 15%
2. SET YOUR WORKFLOW STEPS
|  |  | Step 1 | Step 2 | Step 3 | Step 4 | Step 5 | Workflow totals
|  | # of minutes per volume | 3 | 1 |  |  | 1 | 5
|  | # of minutes per 10 pages |  | 1.5 | 1 |  | 1 | 3.5
|  | # of personnel (FTE) | 4 | 4 | 5 |  | 2 | 15
|  | annual gross salary per FTE | 42000 | 18000 | 36000 |  | 24000
|  | time cost in days (incl. QA) | 5.3906 | 406.0938 | 215.625 | 0 | 542.6562 | 1169.7656
|  | overall personnel costs | 4116.4773 | 132903.4091 | 176420.4545 | 0 | 118397.7273 | 431838.0682
|  | outsourcing / 3rd party costs |  |  |  | 150000 |  | 150000
3. CALCULATION REPORT
total man-days in project | 1169.7656
total project duration in days | 547.6562
total project duration in years | 2.4893
total storage req. in Tb. | 180
total staff costs | 431838.0682
total outsorcing costs | 150000
total storage costs | 90000
total costs | 671838.0682 |  | IMPACT is supported by the European Community under the Information and Communication Technologies Theme of the
costs per page | 0.1493 |  | Seventh Framework Programme. The project is coordinated by the National Library of the Netherlands.
Note on B8: Note: The total number of the volumes you plan to digitise.
Note on B9: Note: The total number of the pages you plan to digitise.
Note on B10: Note: Average storage requirement in megabytes for each page. Depending on the file format this parameter may vary. Please refer to the IMPACT Storage Estimator for more detailed information.
Note on B11: Note: The technologies needed for an appropriate storage solution may vary. Simple hard-drive space can meet the needs of short-termed digitisation projects whereas the storage for a long-term mass digitisation enterprise must achieve greater levels of performance, reliability, and/or larger data volume sizes. The costs inevitably increase with the complexity of the solution.
Note on B12: Note: To give a realistic staff and time cost estimation it is essential to have information about the effective working period. The number of public holidays and paid leave days differ for each institution and country.
Note on B13: Note: To give a realistic staff and time cost estimation it is essential to have information about the effective working period. The number of public holidays and paid leave days differ for each institution and country.
Note on B14: Note: As a part of the quality assurance some steps in the digitisation workflow might need to be repeated, thus increasing the overall costs. Please enter the percentage of the overhead which is likely to be caused by the rollbacks. As a general rule experienced personnel cause less rollbacks.
Note on E16: Note: A digitisation workflow will start by establishing the nature of the content to be delivered, and the form (and functions) of its delivery. Assessment and preparation of the source material is usually performed by experienced librarians for each volume in the collection to be digitised. The image capture is performed page-by-page by less-skilled personnel. Due to the monotonus nature of this step it is recommend working in half day shifts in order to keep the error rate in an acceptable level. Trained personnel with retouching skills are often required for the optimisation of the captured images. Yet automated execution of some of the optimisation processes like border-removal, colour adjustment, dewarping is possible. Workflow steps (full-text capture et al.) can partially or fully be automated (OCR) or outsourced. In this case please leave the annual salary field blank. It is also recommended to run a few tests in order to estimate the time cost for each step, since the values can vary for each organisation, source material, hardware and personnel. Please refer to Workflow Modeller for detailed information on digitisation workflows.
Note on E18: Note: Time needed in minutes to fullfill each step in the digitisation workflow (per volume)
Note on E19: Note: Time needed in minutes to fullfill each step in the digitisation workflow (per ten pages)
Note on E20: Note: Number of full-time equivalents available for each step in the workflow
Note on E21: Note: The annual gross salary per FTE (in €).
Note on E22: Note: The estimated time cost in days including the quality assurance overhead. Preferablly the time cost should be similiar for each step for an ideal time cost optimisation
Note on E23: Note: For each step overall salary costs (in €) will be calculated automatically.
Note on E24: Note: One or more workflow steps (i.e. image capture or full-text capture) can be partially or fully performed by service providers.
This tool is released under a
Creative Commons License:
Attribution-NonCommercial-
ShareAlike 3.0 Unported
We hope that the use of this tool will be self-explanatory, however, if you would like any further support in its use, please contact the IMPACT HelpDesk at www.impact-project.eu/helpdesk.
Although great care was taken in producing this cost estimator, you use it at your own risk. IMPACT can not guarantee the absence of errors or omissions in this tool. If you find any mistakes, please help us improve the tool by either leaving feedback with the HelpDesk or by contacting the authors at impact@sub.uni-goettingen.de
This tool will estimate the overall cost of undertaking a digitisation project. To use it, please fill out the light green cells in Section 1 and then Section 2.